## Sheet1
Sr. No. | Task/Milestone | Assigned To | Effort | Start Date | End Date | Status |  | Remarks/Expectations
Phase 1 (Running the data without fine tuning in the existing architectures) :
| Share all the existing code |  |  |  |  | Complete
| Understand SSD Architecture | Vijin |  | 2018-03-01 | 2018-03-10 | Complete |  | 1. Understand the research papers and find the github code for the network, if required convert to Pytorch code and run on a very small dataset 2. Identify the annotations template and if it matches with standard templates of our proposed dataset
| Understand Faster-RCNN | Chandra |  | 2018-03-01 | 2018-03-18 | In Progress | 2018-03-30
| Understand Mask R-CNN | Atul |  | 2018-03-01 | 2018-03-18 | Abandon
| Undersand R-FCN | Atul |  | 2018-03-11 | 2018-03-25 | Complete
| Identify annotation templates for existing data sets | Vijin |  | 2018-03-11 | 2018-03-18 | Complete |  | Dataset -1 & Dataset - 2
| Scripts to convert the annotations to common template | Vijin |  | 2018-03-11 | 2018-03-18 | In Progress | 2018-03-30 | Dataset - 1
| Scripts to convert videos into frames | Vijin |  | 2018-03-11 | 2018-03-18 | Complete |  | Dataset -1 & Dataset - 2
| Execute on any one standard Dataset | [6 empty] | Dataset - 1
| SSD | Vijin |  | 2018-03-25 | 2018-04-01 | To Be Started
| Faster R-CNN | Chandra |  | 2018-03-25 | 2018-04-01 | To Be Started
| R-FCN | Atul |  | 2018-03-25 | 2018-04-01 | To Be Started
| Milestone 1 complete |  |  | 2018-03-31 | 2018-03-31
Phase 2 (Fine tuning existing architectures to suit our datasets for better accuracy):
Try to fine tune image classification layer(Resnet/VGG) to suit our dataset using transfer learning.
Fine tuned models needs to be incorporated in SSD/Faster R-CNN/Mask R-CNN and analyse accuracy.
| Milestone 2 complete |  |  | 2018-04-15 | 2018-04-15
Phase 3 :
Architecture enhancements. (Not clear what to do at this point).
Running one complex dataset (Stanford drone data).
| Milestone 2 complete |  |  | 2018-04-15 | 2018-04-15
Running code on py 3.6