## Sheet1
Sr. No. | Task/Milestone | Assigned To | Effort | Start Date | End Date | Status |  | Remarks/Expectations
Phase 1 (Running the data without fine tuning in the existing architectures) :
| Share all the existing code |  |  |  |  | Complete
| Understand SSD Architecture | Vijin |  | 2018-03-01 | 2018-03-10 | Complete |  | 1. Understand the research papers and find the github code for the network, if required convert to Pytorch code and run on a very small dataset 2. Identify the annotations template and if it matches with standard templates of our proposed dataset
| Understand Faster-RCNN | Chandra |  | 2018-03-01 | 2018-03-18 | Complete
| Understand Mask R-CNN | Atul |  | 2018-03-01 | 2018-03-18 | Abandon
| Undersand R-FCN | Atul |  | 2018-03-11 | 2018-03-25 | Complete
| Identify annotation templates for existing data sets | Vijin |  | 2018-03-11 | 2018-03-18 | Complete |  | Dataset -1 & Dataset - 2
| Scripts to convert the annotations to common template | Vijin |  | 2018-03-11 | 2018-03-18 | Complete |  | Dataset - 1
| Scripts to convert videos into frames | Vijin |  | 2018-03-11 | 2018-03-18 | Complete |  | Dataset -1 & Dataset - 2
| Execute on any one standard Dataset | [6 empty] | Dataset - 1
| SSD | Vijin |  | 2018-03-25 | 2018-04-01 | Complete | 2018-04-10 | Train and test on one dataset. Evaluate the results with mAP
| Faster R-CNN | Chandra |  | 2018-03-25 | 2018-04-01 | Complete | 2018-04-22
| R-FCN | Atul |  | 2018-03-25 | 2018-04-01 | Complete | 2018-04-10
| Understand next steps in phase2 : Meeting with joseph | All |  | 2018-04-08 | 2018-04-10 | Complete | 2018-04-12
| Milestone 1 complete |  |  | 2018-03-31 | 2018-03-31
Phase 2 (Fine tuning existing architectures to suit our datasets for better accuracy):
| Chang SSD for 2 class model (Train and Test) | Vijin |  |  |  | Complete
| Pascal VOC Annotation change for 2 class model | Vijin |  |  | 2018-04-22 | Complete
| Train and Test VOC 2 Class Model | Vijin |  |  | 2018-04-24 | Complete
| Test Mini drone with VOC train Model | Vijin |  |  | 2018-04-29 | Complete
| Test Okutama with VOC train Model | Vijin |  |  | 2018-04-29 | Complete
| Train and Test Mini Drone Class Model | Vijin |  |  |  | Complete
| Train and Test Okutama Class Model | Vijin |  |  | 2018-04-30 | In Progress
| Evaluation Faster RCNN with Vijin's Method | Chandra |  |  | 2018-04-22 | On Hold
| Change Faster R-CNN for 2 class model (Train and Test) | Chandra |  |  | 2018-04-24 | Complete
| Train and Test VOC 2 Class Model | Chandra |  |  | 2018-04-25 | Complete
| Test Mini drone with VOC train Model | Chandra |  |  | 2018-04-29 | Complete
| Test Okutama with VOC train Model | Chandra |  |  | 2018-04-29 | In Progress | 2018-05-03
| Train and Test Mini Drone Class Model | Chandra |  |  | 2018-04-30 | Complete
| Train and Test Okutama Class Model | Chandra |  |  | 2018-04-30 | Complete
| Change RFCN for 2 class model (Train and Test) | Atul |  |  |  | Complete
| Error Fixed (RFCN) | Atul |  |  |  | Complete
| Evaluation RFCN with Vijin's Method | Atul |  |  | 2018-04-22 | On Hold
| Train and Test VOC 2 Class Model | Atul |  |  | 2018-04-24 | Complete
| Test Mini drone with VOC train Model | Atul |  |  | 2018-04-29 | Complete
| Test Okutama with VOC train Model | Atul |  |  | 2018-04-29 | Complete
| Train and Test Mini Drone Class Model | Atul |  |  | 2018-04-30 | Complete
| Train and Test Okutama Class Model | Atul |  |  | 2018-04-30 | In Progress
| Prepare Report for submission | Vijin, Chandra, Atul |  |  | 2018-04-24 | Complete
| Finalize the model - SSD | Vijin, Chandra, Atul |  |  | 2018-05-01 | To be started
| Understand SSD - Chandra to share | Atul, Chandra |  |  | 2018-05-04 | Complete
| Vijin to share code and walk through | Vijin, Chandra, Atul |  |  | 2018-05-05 | Complete
| Update the Results File | Atul |  |  | 2018-05-14 | In Progress
| Training and testing on okutama dataset. | Vijin |  |  | 2018-05-16 | In Progress
| Incremental training code needs to be written | Vijin |  |  | 2018-05-15 | Complete
| Mean for 3 channels for train data of okutama and mini drone for SSD training | Chandra |  |  | 2018-05-16 | In Progress | 2018-05-18
| Fine tuning voc person 2 class model with mini drone data | Atul |  |  | 2018-05-16 | In Progress | 2018-05-18
| Create validation set from test to check how training performs | Vijin |  |  | 2018-05-19 | In Progress
SSD Fine Tuning
| Train with 10000 iterations on Okutama | Atul
| Test without Okutama Learning (to get baselines) | Atul
Test with new model on Okutama
Repeate for few more 10000 ones
Identifying best hyper parameters for mini drone model.
Transfer learning okutama dataset with mini drone trained model
Feature fusion in SSD
Increasing no of boxes in earlier feature maps
Reducing the size, aspect ratios of boxes