## Sheet1
Sr. No. | Task/Milestone | Assigned To | Effort | Start Date | End Date | Status |  | Remarks/Expectations
Phase 1 (Running the data without fine tuning in the existing architectures) :
| Share all the existing code |  |  |  |  | Complete
| Understand SSD Architecture | Vijin |  | 2018-03-01 | 2018-03-10 | Complete |  | 1. Understand the research papers and find the github code for the network, if required convert to Pytorch code and run on a very small dataset 2. Identify the annotations template and if it matches with standard templates of our proposed dataset
| Understand Faster-RCNN | Chandra |  | 2018-03-01 | 2018-03-18 | Complete
| Understand Mask R-CNN | Atul |  | 2018-03-01 | 2018-03-18 | Abandon
| Undersand R-FCN | Atul |  | 2018-03-11 | 2018-03-25 | Complete
| Identify annotation templates for existing data sets | Vijin |  | 2018-03-11 | 2018-03-18 | Complete |  | Dataset -1 & Dataset - 2
| Scripts to convert the annotations to common template | Vijin |  | 2018-03-11 | 2018-03-18 | Complete |  | Dataset - 1
| Scripts to convert videos into frames | Vijin |  | 2018-03-11 | 2018-03-18 | Complete |  | Dataset -1 & Dataset - 2
| Execute on any one standard Dataset | [6 empty] | Dataset - 1
| SSD | Vijin |  | 2018-03-25 | 2018-04-01 | Complete | 2018-04-10 | Train and test on one dataset. Evaluate the results with mAP
| Faster R-CNN | Chandra |  | 2018-03-25 | 2018-04-01 | Complete | 2018-04-22
| R-FCN | Atul |  | 2018-03-25 | 2018-04-01 | Complete | 2018-04-10
| Understand next steps in phase2 : Meeting with joseph | All |  | 2018-04-08 | 2018-04-10 | Complete | 2018-04-12
| Milestone 1 complete |  |  | 2018-03-31 | 2018-03-31
Phase 2 (Fine tuning existing architectures to suit our datasets for better accuracy):
| Chang SSD for 2 class model (Train and Test) | Vijin |  |  |  | Complete
| Pascal VOC Annotation change for 2 class model | Vijin |  |  | 2018-04-22 | Complete
| Train and Test VOC 2 Class Model | Vijin |  |  | 2018-04-24 | In Progress
| Test Mini drone with VOC train Model | Vijin |  |  | 2018-04-29 | In Progress
| Test Okutama with VOC train Model | Vijin |  |  | 2018-04-29 | In Progress
| Train and Test Mini Drone Class Model | Vijin |  |  |  | Complete
| Train and Test Okutama Class Model | Vijin |  |  | 2018-04-30 | In Progress
| Evaluation Faster RCNN with Vijin's Method | Chandra |  |  | 2018-04-22 | In Progress
| Change Faster R-CNN for 2 class model (Train and Test) | Chandra |  |  | 2018-04-24 | Complete
| Train and Test VOC 2 Class Model | Chandra |  |  | 2018-04-25 | In Progress
| Test Mini drone with VOC train Model | Chandra |  |  | 2018-04-29 | In Progress
| Test Okutama with VOC train Model | Chandra |  |  | 2018-04-29 | In Progress
| Train and Test Mini Drone Class Model | Chandra |  |  | 2018-04-30 | In Progress | Train Complete
| Train and Test Okutama Class Model | Chandra |  |  | 2018-04-30 | In Progress
| Change RFCN for 2 class model (Train and Test) | Atul |  |  |  | Complete
| Error Fixed (RFCN) | Atul |  |  |  | Complete
| Evaluation RFCN with Vijin's Method | Atul |  |  | 2018-04-22 | Complete
| Train and Test VOC 2 Class Model | Atul |  |  | 2018-04-24 | In Progress
| Test Mini drone with VOC train Model | Atul |  |  | 2018-04-29 | In Progress
| Test Okutama with VOC train Model | Atul |  |  | 2018-04-29 | In Progress
| Train and Test Mini Drone Class Model | Atul |  |  | 2018-04-30 | In Progress | Train Complete
| Train and Test Okutama Class Model | Atul |  |  | 2018-04-30 | In Progress
| Prepare Report for submission | Vijin, Chandra, Atul |  |  | 2018-04-24 | In Progress
| Finalize the model | Vijin, Chandra, Atul |  |  | 2018-05-01 | To be started